## Green
Player/HUD
Make It Awesome
DOON
Starting Date: | 2024-10-02 |  |  |  | KEY | [6 empty] | Scrolling increment: | [5 empty] | 30
[5 empty] | Completed | [6 empty] | Planned | [8 empty] | This Week
 | time axis 2024-11-01 to 2024-12-26
Milestone description | Hours Predicted | Progress | Start | Hours Completed | time axis 2024-11-01 to 2024-12-26
Player Development
Player Design/Animations | 7 | 65% | 2024-10-02 | 4 | bar: 2024-11-01 to 2024-11-07
Level1/2 Movement | 5 | 50% | 2024-10-09 | 2 | bar: 2024-11-08 to 2024-11-12
Interaction | 5 | 20% | 2024-10-11 | 1 | bar: 2024-11-13 to 2024-11-17
HUD | 5 | 55% | 2024-10-14 | 3 | bar: 2024-11-18 to 2024-11-22
Level 3 Controls | 6 | 0% | 2024-10-20 | 0 | bar: 2024-11-23 to 2024-11-28
Mobile Controls | 5 | 0% | 2024-10-30 | 0 | bar: 2024-11-29 to 2024-12-03
Testing | 4 | 0% | 2024-11-05 | 0 | bar: 2024-12-04 to 2024-12-07
Installation | 2 | 0% | 2024-11-25 | 0 | bar: 2024-12-08 to 2024-12-09
Total: | 39 |  |  | 10
To add more data, Insert new rows ABOVE this one